# Business Case

NOTE: This is a completed sample for reference. Replace all content with your actual project details.

| Document Title | Order Management System Modernization — Business Case |
| --- | --- |
| Project Name | OMS Modernization Project |
| Prepared By | Ken Tanaka (IT Consultant) |
| Date | September 1, 2025 |
| Version | v1.0 |
| Approver | President Suzuki (CFO) |

# 1. Executive Summary

The current Order Management System (OMS) has reached end-of-vendor-support in 2027 and relies heavily on manual processing, consuming approximately 2,400 staff-hours annually. This project proposes migrating to a modern SaaS-based OMS to achieve annual cost savings of JPY 36 million and a 50% reduction in order lead time. The total investment is JPY 120 million, with an estimated payback period of 3.3 years and a 3-year ROI of 195%. We respectfully request approval by October 31, 2025, to enable a project start of November 1.

# 2. Problem Statement / Opportunity

Current challenge: The aging OMS requires manual intervention across order entry, inventory check, and invoice issuance, consuming approximately 2,400 staff-hours and JPY 18 million in labor costs annually.

Risk of inaction: Vendor support ends in 2027. Post-EOL system failures would carry unpredictable recovery costs and pose significant business continuity risk.

Business opportunity: A modern OMS will shorten order lead time, improve inventory accuracy, and is expected to increase annual revenue by 2–3% through improved customer satisfaction.

# 3. Objectives & Scope

| Objective | Success Metric | Target Date |
| --- | --- | --- |
| Automate order processing | Reduce manual effort from 2,400h to under 600h/year | June 2026 |
| Shorten order lead time | Reduce average lead time from 5 days to under 2.5 days | June 2026 |
| Automate invoice issuance | Reduce manual invoice rate from 80% to under 10% | September 2026 |

In scope: Order management, inventory management, invoice issuance, ERP integration (core system)

Out of scope: HR system, expense management system, e-commerce integration (Phase 2 or later)

# 4. Options Analysis

| Option | Description | Investment | Expected Benefit | Risk | Recommended |
| --- | --- | --- | --- | --- | --- |
| Option A: Do Nothing | Maintain current system | JPY 6M/yr | None | High (EOL 2027) |  |
| Option B: Partial Enhancement | Add features to existing system | JPY 50M | Limited | Medium |  |
| Option C: New System (Recommended) | SaaS OMS migration | JPY 120M | JPY 36M/yr savings | Low–Med | ✅ |

# 5. Financial Analysis

| Item (JPY million) | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- |
| Initial Investment | 120 | — | — | 120 |
| Operating Costs | 6 | 6 | 6 | 18 |
| Cost Savings | 18 | 36 | 36 | 90 |
| Net Benefit | △108 | 30 | 30 | △48 |

Payback Period: approx. 3.3 years   ROI (3-year): 195%   NPV (5% discount rate): approx. JPY 28M

# 6. Risk Assessment

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Business disruption during migration | Medium | High | Phased migration with 1-month parallel operation |
| Requirement definition delays | Medium | Medium | Engage external consultant; fix timeline milestones |
| Data migration quality issues | Low | High | Full-data validation and 2 migration rehearsals before go-live |

# 7. Implementation Plan

| Phase | Description | Timeline | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Requirements | Current state analysis & requirements definition | Nov 2025 – Jan 2026 | BRD, System Requirements |
| Phase 2: Design & Build | System design, development, and testing | Feb – Mar 2026 | Test Report |
| Phase 3: Migration & Go-Live | Data migration, UAT, production cutover | April 2026 | Cutover Report |

# 8. Recommendation & Approval

Recommended option: Option C — SaaS OMS Modernization. The 3.3-year payback period and 195% ROI exceed internal hurdle rates (4 years / 150%), and the project eliminates the EOL risk.

Approval requested by: October 31, 2025 (project kickoff scheduled for November 1)

Next steps upon approval: Execute kickoff on November 1 and sign the external consultant agreement.