# Change Request Document

Project: E-Commerce Renewal — Payment API Migration (Sample)

# Change Overview

| Change ID | CR-2025-042 |
| --- | --- |
| Change Title | Migrate Payment API from Stripe v2 to Stripe v3 |
| Requested By | Hanako Yamada (Backend Engineer) |
| Request Date | September 1, 2025 |
| Change Category | Normal Change |
| Priority | High |
| Planned Implementation Date | September 20, 2025 — 02:00 to 04:00 (Maintenance Window) |

# Reason & Impact Assessment

Reason for Change: Stripe v2 reaches EOL in December 2025; migration to v3 is required to maintain payment processing

Risk of Not Changing: Post-EOL payment errors will directly impact sales revenue

Affected Systems / Features: E-commerce checkout, order confirmation API, admin sales report dashboard

End-User Impact: Payment processing unavailable during maintenance window (approx. 2 hours)

# Change Details & Implementation Steps

| Step | Task | Owner | Duration |
| --- | --- | --- | --- |
| 1 | Verify Stripe v3 behavior in staging environment | Yamada | 30 min |
| 2 | Replace production API keys with Stripe v3 credentials | Yamada | 15 min |
| 3 | Validate payment flow and Webhook with test transactions | Yamada / Suzuki | 30 min |
| 4 | Verify sales report display in admin dashboard | Tanaka | 15 min |
| 5 | If no issues, lift maintenance and submit completion report | Yamada | 10 min |

# Risks & Mitigation

| Risk | Severity | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Webhook signature validation error | High | Medium | Pre-validated in staging. Rollback if error occurs |
| Test payment failure | Medium | Low | Multiple backup test cards prepared for validation |

# Rollback Plan

| Rollback Trigger | Procedure | Decision Maker | Estimated Time |
| --- | --- | --- | --- |
| 3 consecutive test payment failures at Step 3 | Revert API keys to v2 and restore configuration files | Hanako Yamada | Within 15 min |

# Approval / Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Change Requester | Hanako Yamada | (Signed) | September 1, 2025 |
| Project Manager | Ichiro Tanaka | (Signed) | September 3, 2025 |
| Change Approver (CAB) | Jiro Suzuki | (Signed) | September 5, 2025 |