## Checklist
■ Basic Information
Project Name |  | Order Management System Modernization
Release Version |  | v2.1.0
Scheduled Release |  | 2025-10-31 23:00 JST
Release Owner |  | Ken Tanaka (Release Manager)
Last Updated |  | 2025-10-30
No. | Category | Check Item | Owner | Date | Status | Notes
1 | Functional | All tests completed in staging environment | Taro Yamada | 2025-10-28 | ✅ OK | All regression tests passed
2 | Functional | All Critical and High defects are closed | Taro Yamada | 2025-10-29 | ✅ OK | No open defects
3 | Functional | UAT sign-off has been obtained | Hanako Suzuki | 2025-10-30 | ✅ OK | Approved by Sales Director
4 | Environment | Environment variables configured for production | Ken Tanaka | 2025-10-30 | ✅ OK
5 | Environment | Database connection verified in production | Ken Tanaka | 2025-10-30 | ✅ OK | Connection test passed
6 | Environment | Database backup completed | Ken Tanaka | 2025-10-30 | ✅ OK | Snapshot taken
7 | Environment | Monitoring and alerting configured | Ken Tanaka | 2025-10-29 | ✅ OK | Datadog configured
8 | Security | All communications are TLS-encrypted | Jiro Sato | 2025-10-28 | ✅ OK | TLS 1.3
9 | Security | Debug logs and test accounts removed | Jiro Sato | 2025-10-29 | ✅ OK
10 | Rollback | Rollback procedure documented and reviewed | Ken Tanaka | 2025-10-28 | ✅ OK | Posted on Confluence
11 | Rollback | Rollback time is within acceptable range | Ken Tanaka | 2025-10-28 | ✅ OK | Est. within 15 min
12 | Communication | Release notification sent to stakeholders | Hanako Suzuki | 2025-10-29 | ✅ OK | All departments notified
13 | Communication | Maintenance notice sent (if applicable) | Hanako Suzuki | 2025-10-29 | N/A | No maintenance window

## Go-No-Go Decision
■ Go/No-Go Decision
Role | Name | Decision | Date & Time | Comments
Release Owner | Ken Tanaka | ✅ Go | 2025-10-31 22:00 | All items OK. Go approved.
Tech Lead | Jiro Sato | ✅ Go | 2025-10-31 21:30 | Rollback procedure confirmed.
Business Owner | Hanako Suzuki | ✅ Go | 2025-10-31 21:45 | UAT complete. Business ready.

## Status Legend
■ Status Legend
Status | Meaning | Action
✅ OK | Verified — no issues | Proceed to next item
❌ NG | Failed or not verified | Resolve and re-check. Consider No-Go
⚠️ Needs Review | Conditional OK | Document risk; decision owner to approve
N/A | Not applicable | State reason in Notes
In Progress | Check in progress | Resolve before release
Pending Approval | Awaiting approval | Contact approver