# Migration Plan

# Migration Overview

| Project Name | OMS Cloud Migration Project |
| --- | --- |
| Target System | OMS v2.3 (on-premises) → SaaS-based OMS v3.0 on AWS |
| Migration Approach | Lift-and-Shift (Phase 1) + Re-architect (Phase 2) |
| Migration Completion Date | September 30, 20XX (production cutover) |
| Migration Owner | Taro Tanaka (Infrastructure Migration Lead) |
| Date Prepared | July 1, 20XX |

# Migration Scope

In Scope: OMS application (Java/Spring Boot), Oracle database (orders, POs, inventory data), web server (Tomcat), batch jobs (15 jobs)

Out of Scope: ERP core (SAP), inventory management system, report output system (handled in separate projects)

# Migration Approach & Architecture

Migration Approach: Phase 1 lift-and-shift to EC2; Phase 2 re-architect to RDS Aurora and ECS

Target Architecture: App Server (ECS Fargate), DB (RDS Aurora MySQL), Batch (AWS Batch), Storage (S3), Network (VPC/ALB)

# Migration Schedule

| Phase | Tasks | Owner | Timeline |
| --- | --- | --- | --- |
| Preparation | AWS environment setup, network config, pre-migration data sync | Infrastructure Team | July–August |
| Rehearsal 1 | Full procedure validation, time measurement, issue identification | Full Migration Team | Mid-August |
| Rehearsal 2 | Post-fix final validation, rollback drill | Full Migration Team | Early September |
| Production Cutover | Cutover execution during maintenance window (Sat 22:00–Sun 06:00) | Full Migration Team | Sep 28 |
| Post-Migration Validation | Validation, performance monitoring, 30-day parallel operation | Operations Team | October |

# Risks & Mitigation

| Risk | Severity | Mitigation | Owner |
| --- | --- | --- | --- |
| Data integrity errors after migration | High | Auto-compare record counts and checksums before/after migration. Stop immediately if discrepancies are found. | DB Team |
| Cutover window overrun | High | Reserve maintenance window at 1.5x rehearsal time. Initiate rollback if cutover exceeds 6 hours. | Migration Lead |
| AWS environment performance shortfall | Medium | Run load tests during rehearsal to confirm 50,000 records/hour at peak capacity. | Infra Team |
| Legacy ERP API connectivity failure | Medium | Pre-validated in integration test environment. Re-verify connectivity on the day before cutover. | App Team |

# Rollback Plan

| Rollback Trigger | Procedure | Decision Maker | Estimated Time |
| --- | --- | --- | --- |
| 3 or more data integrity errors within 6 hours of migration start | 1. Stop migration immediately 2. Revert DNS to legacy OMS 3. Restore legacy DB access 4. Verify all system connectivity | Taro Tanaka (Migration Lead) | Within 2 hours |
| Core functions (order receipt, PO) fail post-migration validation | 1. Immediately notify stakeholders 2. Execute rollback to legacy environment 3. Schedule root-cause analysis and re-migration on next business day | Dept. Manager Sato (IT Infra) | Within 4 hours |