# Test Plan

Project: E-Commerce Loyalty Points Feature — Test Plan Sample

| Project | E-Commerce Loyalty Points Feature |
| --- | --- |
| Version | 1.0 |
| Author | Saburo Suzuki (QA Lead) |
| Date | September 10, 2025 |
| Status | Approved |

# Test Overview & Objectives

This Test Plan defines the testing activities required to ensure the quality of the Loyalty Points feature (point accrual on purchase, redemption, and balance inquiry) prior to its production release. Testing covers all phases from unit testing through UAT. The release decision will be based on zero Critical/High defects and Business Owner sign-off.

# Scope

## In Scope

Point accrual logic (award on order confirmation, deduction on return)

Point redemption and payment integration (integration testing with accounting system)

My Page: point balance and transaction history display

User Acceptance Testing (UAT)

## Out of Scope

Existing payment and cart features (no changes; excluded from testing)

Security penetration testing (scheduled separately for Q4)

# Test Types & Approach

| Test Type | Objective | Responsible | Timing |
| --- | --- | --- | --- |
| Unit Test | Verify point calculation logic | Dev Team | Complete by Sep 15 |
| Integration Test | Verify connectivity with accounting system | Dev Team | Sep 18–20 |
| System Test | End-to-end: purchase through point accrual | QA Team | Sep 22–25 |
| UAT | Confirm business requirements are met | Business Owner | Sep 27–30 |
| Regression Test | Verify no impact on existing features | QA Team | Before release |

# Test Environment

| Environment | Purpose | Owner |
| --- | --- | --- |
| Development (Dev) | Developer testing during build | Dev Team |
| Test / QA | Integration and system test execution | QA Team |
| Staging | UAT and final verification | Infra Team |

# Test Schedule & Milestones

| Milestone | Target Date | Owner |
| --- | --- | --- |
| Test Plan approved | Sep 10 | PM |
| Test cases finalized | Sep 14 | QA Team |
| Unit testing complete | Sep 15 | Dev Team |
| Integration testing complete | Sep 20 | Dev Team |
| System testing complete | Sep 25 | QA Team |
| UAT sign-off | Sep 30 | Business Owner |
| Production release | Oct 3 | All Teams |

# Entry & Exit Criteria

## Entry Criteria

Testing from the previous phase is complete

The test environment is available and stable

Test data for the loyalty points feature (accrual rate, cap values) has been prepared

## Exit Criteria

95% or more of planned test cases have been executed

All Critical and High-priority defects are closed

Business Owner sign-off has been obtained

## Defect Priority Definitions

| Priority | Definition |
| --- | --- |
| Critical | Point calculation error or revenue impact — operations cannot continue |
| High | Point balance not displayed correctly; key feature defect with no workaround |
| Medium | UI misalignment; feature works but not as expected; workaround exists |
| Low | Minor typo or design issue; no business impact |