## Test Case Log
■ Basic Information
Project Name |  |  | Order Management System Modernization
UAT Phase |  |  | UAT Phase 2
Test Period |  |  | 2025-10-15 – 2025-10-28
Test Owner |  |  | Hanako Suzuki
Last Updated |  |  | 2025-10-28
Test Case ID | Feature | Test Summary | Test Steps | Expected Result | Actual Result | Status | Tester | Test Date | Bug ID | Notes
TC-001 | Login | Successful login with valid credentials | 1. Open login page 2. Enter valid ID and password 3. Click Login | User is redirected to the home screen | Redirected to home screen as expected | ✅ Pass | Taro Yamada | 2025-10-16
TC-002 | Login | Login attempt with invalid password | 1. Open login page 2. Enter invalid password 3. Click Login | Error message is displayed | Error message displayed correctly | ✅ Pass | Taro Yamada | 2025-10-16
TC-003 | Order Entry | Create a new order | 1. Navigate to order entry screen 2. Enter required fields 3. Click Save | Order is saved and appears in the order list | Page did not redirect to list after save | ❌ Fail | Hanako Suzuki | 2025-10-17 | BUG-042 | Redirect bug. Fix required.
TC-004 | Order Entry | Validation on missing required fields | 1. Navigate to order entry screen 2. Leave required fields blank 3. Click Save | Validation error is displayed | Validation error displayed as expected | ✅ Pass | Hanako Suzuki | 2025-10-17
TC-005 | Invoice Export | Export invoice as PDF | 1. Select a target order from the order list 2. Click Export Invoice button | PDF is generated correctly |  | ⚠️ Blocked | Ken Tanaka | 2025-10-18 |  | Test data not ready. DBA to set up by 10-21.
TC-006 | Access Control | Admin-only access to settings screen | 1. Log in as a general user 2. Directly enter the settings URL | Access denied error is displayed | 403 error displayed correctly | ✅ Pass | Ken Tanaka | 2025-10-20

## Sign-off Record
■ Sign-off Record
Role | Name | Decision | Date & Time | Comments
UAT Owner | Hanako Suzuki | ✅ Approved | 2025-10-28 17:00 | Approved after BUG-042 fix confirmed
Business Owner | General Manager | ✅ Approved | 2025-10-28 17:30 | All business requirements met
Project Manager | Ken Sato | ✅ Approved | 2025-10-28 18:00 | No issues with release decision

## Status Legend
■ Status Legend
Status | Meaning | Action
✅ Pass | Test passed — actual matches expected | Proceed to next test case
❌ Fail | Test failed — actual does not match expected | Log bug ID and await retest
⚠️ Blocked | Cannot execute — prerequisite not ready | Document cause and expected unblock date in Notes
⬜ Not Tested | Not yet executed | Schedule test execution
Pending Retest | Awaiting retest after fix | Re-execute after fix is deployed