## WBS
NOTE: This is a completed sample for reference. Replace all content with your actual project details.
Project Name | Order Management System Modernization
Author | Jane Smith (Project Manager)
Last Updated | June 1, 2026
WBS No. | Task / Deliverable | Owner | Start Date | End Date | Est. Effort (h) | Actual Effort (h) | Progress (%) | Status
1.0 | Order Management System Modernization
1.1 | Requirements Phase |  | Jun 2 | Jun 20 | 60 | 60 |  | Completed
1.1.1 | Requirements Gathering Report |  | Jun 2 | Jun 6 |  |  |  | Completed
1.1.1.1 | Conduct requirements gathering | J. Smith | Jun 2 | Jun 4 | 8 | 10 | 100% | Completed
1.1.1.2 | Prepare meeting minutes and report | J. Smith | Jun 5 | Jun 6 | 4 | 4 | 100% | Completed
1.1.2 | Business Requirements Document (BRD) |  | Jun 9 | Jun 20 |  |  |  | Completed
1.1.2.1 | Draft BRD | M. Johnson | Jun 9 | Jun 13 | 16 | 18 | 100% | Completed
1.1.2.2 | Stakeholder review and approval | J. Smith | Jun 16 | Jun 20 | 8 | 8 | 100% | Completed
1.2 | Design Phase |  | Jun 23 | Jul 18 | 80 | 45 |  | In Progress
1.2.1 | Basic Design Document |  | Jun 23 | Jul 11 |  |  |  | In Progress
1.2.1.1 | System architecture design | S. Lee | Jun 23 | Jun 30 | 24 | 24 | 100% | Completed
1.2.1.2 | UI / screen design | D. Chen | Jul 1 | Jul 7 | 16 | 8 | 50% | In Progress
1.2.1.3 | Database design | M. Johnson | Jul 7 | Jul 11 | 16 | 0 | 0% | Not Started
1.2.2 | ERP API Design Document |  | Jul 14 | Jul 18 |  |  |  | Not Started
1.2.2.1 | API specification document | S. Lee | Jul 14 | Jul 18 | 24 | 0 | 0% | Not Started
1.3 | Development Phase |  | Jul 22 | Sep 12 | 160 | 0 |  | Not Started
1.3.1 | Order Management Feature Development |  | Jul 22 | Aug 22 |  |  |  | Not Started
1.3.1.1 | Order registration and edit feature | D. Chen | Jul 22 | Aug 1 | 40 | 0 | 0% | Not Started
1.3.1.2 | ERP integration module | M. Johnson | Aug 4 | Aug 22 | 40 | 0 | 0% | Not Started
1.3.1.3 | Unit testing | D. Chen | Aug 25 | Aug 29 | 24 | 0 | 0% | Not Started
1.4 | Test Phase |  | Sep 1 | Sep 26 | 80 | 0 |  | Not Started
1.4.1.1 | Integration testing | M. Johnson | Sep 1 | Sep 12 | 24 | 0 | 0% | Not Started
1.4.1.2 | UAT execution and sign-off | J. Smith | Sep 16 | Sep 26 | 16 | 0 | 0% | Not Started
1.5 | Release Phase |  | Sep 30 | Oct 3 | 20 | 0 |  | Not Started
1.5.1.1 | Production deployment | S. Lee | Sep 30 | Oct 1 | 8 | 0 | 0% | Not Started
1.5.1.2 | Release verification and approval | J. Smith | Oct 2 | Oct 3 | 4 | 0 | 0% | Not Started