# Project Closure Report

Project: E-Commerce Platform Migration (Sample)

| Project Name | E-Commerce Platform Migration |
| --- | --- |
| Period | April 7 – August 29, 2026 |
| Project Manager | Hanako Yamada |
| Date | September 5, 2026 |
| Status | Closed |

# Project Summary

Objective: Modernize the legacy e-commerce platform and improve page load speed by 50%

Scope: Frontend, backend, and database migration. Mobile app was out of scope

Team: 6 members (PM, Tech Lead, 2 Backend, 1 Frontend, 1 QA)

# Scope Achievement

| Scope Item | Planned | Actual | Status | Notes |
| --- | --- | --- | --- | --- |
| Product list and detail pages | July 31 | July 28 | Achieved | 3 days early |
| Cart and checkout features | July 31 | August 5 | Achieved | 5-day delay |
| Database migration | August 22 | August 22 | Achieved | — |
| Production release | August 29 | August 29 | Achieved | On schedule |
| Points feature | August 29 | Next phase | Not achieved | Scope change approved |

# Deliverables

| No. | Deliverable | Delivery Date | Recipient | Approver |
| --- | --- | --- | --- | --- |
| 1 | Production e-commerce site (v2.5.0) | August 29 | Jiro Takahashi (Client) | Jiro Takahashi |
| 2 | System design and API specification docs | August 22 | Jiro Takahashi | Jiro Takahashi |
| 3 | Test results report | August 26 | Jiro Takahashi | Hanako Yamada |
| 4 | Operations handover guide and Runbook | August 29 | Jiro Takahashi | Jiro Takahashi |

# Budget and Schedule Actuals

| Item | Planned | Actual | Variance | Reason |
| --- | --- | --- | --- | --- |
| Budget | 8M JPY | 8.35M JPY | +350K JPY | Additional checkout spec requirements |
| Duration | 5 months | 5.2 months | 1-week delay | Checkout spec change |
| Effort | 24 person-months | 26 person-months | +2 person-months | Additional testing scope |

# Issues and Risks Review

| No. | Issue / Risk | Response | Outcome | Prevention |
| --- | --- | --- | --- | --- |
| 1 | Payment API spec change caused 1-week delay | Adjusted scope and replanned sprints | Resolved | Strengthen change management process |
| 2 | Test environment instability delayed QA phase | Set up an additional production-equivalent environment | Resolved | Document test environment setup in Runbook |

# Lessons Learned

What worked well: Weekly retrospectives enabled early issue detection and continuous improvement (continue in future projects)

What needs improvement: Include external API spec change risk in the change management plan from project start

Recommendations: Include test environment setup procedures in the Runbook and prepare it at project kickoff