# Go-Live Checklist

| Project Name | [Project Name] |
| --- | --- |
| Release Window | [Date] 02:00–06:00 JST |
| Release Lead | [Name] |
| Participants | [Name], [Name], [Name] |
| Rollback Deadline | [Date] 05:00 JST |
| Go/No-Go Decision Owner | Project Manager: [Name] |

# Pre-Go-Live Checklist

| No. | Task | Owner | Completed At | Verified By |
| --- | --- | --- | --- | --- |
| 1 | Release notification sent to all stakeholders | [Name] |  | [Name] |
| 2 | Backup completed and restore procedure verified | [Name] |  | [Name] |
| 3 | Regression tests passed on staging environment | [Name] |  | [Name] |
| 4 | Rollback procedure reviewed by the full team | [Name] |  | [Name] |
| 5 | Monitoring alert thresholds adjusted for production | [Name] |  | [Name] |
| 6 | Support team briefed on release timing and scope | [Name] |  | [Name] |

# Cutover Checklist

| No. | Task | Owner | Planned | Completed At | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Maintenance mode enabled and confirmed | [Name] | 02:00 |  |  |
| 2 | Final database backup taken | [Name] | 02:05 |  |  |
| 3 | New version deployed | [Name] | 02:20 |  |  |
| 4 | Data migration script executed | [Name] | 02:50 |  |  |
| 5 | DNS / load balancer switched | [Name] | 03:35 |  |  |
| 6 | Smoke tests completed | [Name] | 03:45 |  |  |

# Post-Go-Live Checklist

| No. | Task | Owner | Completed At | Verified By |
| --- | --- | --- | --- | --- |
| 1 | Error rate, latency, and CPU within normal range | [Name] |  | [Name] |
| 2 | No unexpected errors found in logs | [Name] |  | [Name] |
| 3 | Key user flows verified | [Name] |  | [Name] |
| 4 | Maintenance mode disabled and service restored | [Name] |  | [Name] |
| 5 | Go-live completion notification sent to stakeholders | [Name] |  | [Name] |
| 6 | Support team notified that service is back online | [Name] |  | [Name] |

# Rollback Criteria

| Trigger | Threshold | Action |
| --- | --- | --- |
| Error rate spike | (e.g., Exceeds 5%) | Initiate rollback immediately |
| Critical feature failure | (e.g., Login, payment, or search is down) | Initiate rollback immediately |
| Smoke test failure | (e.g., Pass rate below 80%) | Escalate to PM for Go/No-Go decision |
| Rollback deadline exceeded | (e.g., After 05:00 JST) | Continue with fix-forward strategy |