# Cost Management Plan

| Project Name | [System] Development Project |
| --- | --- |
| Prepared By | [Name], PM |
| Date | [Date] |
| Version | v1.0 |
| Approved By | [Name], PMO |

# Cost Estimation Approach

| Item | Details |
| --- | --- |
| Estimation Method | Bottom-up estimation (task-level effort × unit rate) |
| Estimation Unit | Person-day (1 person-day = 8 hours) |
| Rate Standards | Internal: ¥[X]/person-day; External: ¥[X]/person-day |
| Buffer | Reserve 10% of total estimate as contingency reserve |
| Currency | JPY. Overseas vendors quoted in USD, converted to JPY |
| Cost Tracking Tool | Excel cost tracker (managed in Confluence) |

# Budget Allocation by Category

| Category | Budget | % | Key Items |
| --- | --- | --- | --- |
| Labor (internal) | ¥[X] | [X]% | PM, dev team, QA effort |
| Labor (external) | ¥[X] | [X]% | External engineers, consultants |
| Infrastructure / cloud | ¥[X] | [X]% | AWS, tools, licenses |
| External services | ¥[X] | [X]% | Security assessment, translation, testing support |
| Contingency reserve | ¥[X] | 10% | Reserve for unforeseen events |
| Total | ¥[X] | 100% |  |

# Cost Monitoring — EVM Metrics

| Metric | Definition | Formula |
| --- | --- | --- |
| PV (Planned Value) | Cost planned to have been spent by this point | Cumulative budget |
| AC (Actual Cost) | Cost actually incurred by this point | Cumulative actuals |
| EV (Earned Value) | Planned cost of work completed by this point | % complete × total budget |
| CV (Cost Variance) | EV − AC (positive = under budget) | EV − AC |
| CPI (Cost Performance Index) | EV / AC (≥1.0 = under budget) | EV ÷ AC |

# Cost Overrun Thresholds and Actions

| Overrun | Action |
| --- | --- |
| Up to +5% of plan | PM analyzes root cause and explains in monthly report |
| +5–10% of plan | Report to PMO; PM prepares recovery plan |
| Over +10% of plan | Escalate to stakeholders; activate cost change management |

# Cost Change Management

| Step | Action | Owner | Deadline |
| --- | --- | --- | --- |
| 1. Detect | Identify cost overrun via monthly report or actual entry | PM | As needed |
| 2. Root Cause Analysis | Identify cause (scope addition, effort increase, rate increase, etc.) | PM + stakeholders | Within 2 business days of detection |
| 3. Recovery Plan | Evaluate options: scope reduction, efficiency improvement, budget request | PM | Within 2 business days of analysis |
| 4. Approval | Present changes to stakeholders and obtain budget change approval | PM + Sponsor | Within 5 business days of recovery plan |
| 5. Update Plan | Reflect approved changes in budget plan and cost tracking sheet | PM | Within 1 business day of approval |