# Procurement Management Plan

| Project Name | [System] Development Project |
| --- | --- |
| Prepared By | [Name], Procurement |
| Date | [Date] |
| Version | v1.0 |
| Approved By | [Name], PM |

# Procurement Requirements

| No. | Item / Service | Type | Est. Cost | Timing | Priority |
| --- | --- | --- | --- | --- | --- |
| 1 | Cloud infrastructure (AWS) | SaaS/IaaS | ¥500K/month | Project start | High |
| 2 | Development support (external engineers) | Staffing | ¥2M/month | Phase 2 start | High |
| 3 | Security assessment | One-time | ¥3M | 3 months before release | Medium |
| 4 | Monitoring tool (Datadog, etc.) | SaaS | ¥300K/month | Testing phase start | Medium |
| 5 | Translation / localization | One-time | ¥1M | After UI design finalized | Low |

# Vendor Selection Process

| Step | Action | Owner | Est. Duration |
| --- | --- | --- | --- |
| 1. Requirements | Finalize procurement requirements and evaluation criteria | PM + Procurement | 1–2 weeks |
| 2. RFP | Send RFP to candidate vendors | Procurement | 1 week |
| 3. Proposals | Receive proposals and quotes from vendors | Procurement | 2–3 weeks |
| 4. Evaluation | Compare and score vendors against evaluation criteria | Evaluation Committee | 1–2 weeks |
| 5. Negotiation | Negotiate terms with the final candidate vendor | PM + Procurement + Legal | 1–2 weeks |
| 6. Contract | Sign the contract and finalize the procurement | PM + Legal | 1 week |

# Vendor Evaluation Criteria

| Criterion | Weight | Evaluation Method |
| --- | --- | --- |
| Technical capability and track record | 30% | Proposal content, past projects, reference checks |
| Cost | 25% | Quote amount, TCO comparison |
| Support | 20% | Response hours, SLA, engineer expertise |
| Security and compliance | 15% | ISO certification, security measures, GDPR compliance |
| Financial stability | 10% | Revenue size, years in business, credit check |

# Contract Management

| Area | Action | Owner | Frequency |
| --- | --- | --- | --- |
| Deliverable review | Confirm deliverables and milestone completion | PM + Procurement | Monthly / at milestones |
| Payment management | Review invoices and process payments | Procurement + Finance | Monthly |
| SLA monitoring | Confirm vendor SLA compliance | Procurement | Monthly |
| Contract change management | Process scope or cost changes via change management | PM + Legal | As needed |
| Contract expiry management | Track contract terms and renewal deadlines | Procurement | Quarterly |

# Procurement Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Vendor bankruptcy or service termination | Low | High | Pre-select alternative vendors; confirm data export procedures |
| Delivery delay | Medium | High | Include penalty clauses in contract; build in buffer time |
| Security incident | Low | High | Require security assessment; include incident response clauses in contract |
| Cost overrun | Medium | Medium | Monthly cost tracking; set budget alert thresholds |
| Vendor lock-in | Medium | Medium | Multi-vendor strategy; ensure data portability |