# Resource Management Plan

| Project Name | [System] Development Project |
| --- | --- |
| Prepared By | [Name], PM |
| Date | [Date] |
| Version | v1.0 |
| Approved By | [Name], PMO |

# Human Resource Plan

| Role | Required Skills | Count | Phase | Source | Monthly Effort |
| --- | --- | --- | --- | --- | --- |
| PM | PMP equivalent, business-level English | 1 | All phases | Internal | 160 hours |
| Tech Lead | Senior Java/Python, 5+ years system design | 1 | Design–Release | Internal | 160 hours |
| Backend Engineer | Mid-level Java/Python, REST API design | 3 | Development–Testing | 2 internal + 1 external | 160 hours each |
| Frontend Engineer | Mid-level React/TypeScript | 2 | Development–Testing | 1 internal + 1 external | 160 hours each |
| Infrastructure Engineer | AWS, Terraform, security design | 1 | Design–Release | Internal | 80 hours |
| QA Engineer | Test design, automation experience | 1 | Testing–Release | Internal | 160 hours |

# Roles and Responsibilities (RACI)

| Task | PM | Tech Lead | Backend | Frontend | Infra | QA |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements | A | R | C | C | I | C |
| System Design | C | A | R | R | R | C |
| Development | I | C | R | R | C | I |
| Infrastructure Setup | C | C | C | I | R/A | I |
| Test Planning | C | C | C | C | I | R/A |
| UAT Coordination | R/A | C | I | I | I | C |
| Release Decision | A | C | I | I | C | C |

# Resource Calendar

| Phase | Duration | PM | Tech Lead | Backend | Frontend | Infra | QA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements | Jan–Feb | ◎ | ◎ | ○ | ○ | △ | △ |
| Design | Mar–Apr | ○ | ◎ | ◎ | ◎ | ◎ | ○ |
| Development | May–Aug | △ | ○ | ◎ | ◎ | ○ | △ |
| Testing | Sep–Oct | ○ | ○ | ◎ | ◎ | ○ | ◎ |
| Migration & Release | Nov | ◎ | ◎ | ○ | ○ | ◎ | ◎ |

# Resource Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Key person sudden departure | Low | High | Document knowledge; designate backup assignees |
| Delay in securing external resources | Medium | High | Order early considering lead times; prepare backup candidates |
| Team member overload | Medium | Medium | Monthly effort review; add headcount or adjust priorities as needed |
| Skill mismatch | Low | Medium | Pre-project skill assessment; prepare OJT plan |
| Concurrent project assignments | Medium | Medium | Clarify dedicated allocation ratio; coordinate with other PMs |